MINUTES OF MEETING CONVENED BY PRINCIPAL SECRETARY, SKILLS DEVELOPMENT & TRAINING DEPARTMENT ON SKILL ACTIVITIES

Date: 1st September 2022 at 10.30 AM

Venue: ITE&C Conference Hall, Secretariat, 4th block

Present:

Chaired by: Sri. Saurabh Gaur, IAS, Principal Secretary for Department of Skills Development & Training

Name of the Officer

- Shri. S. Satyanarayana, IAS, MD&CEO, APSSDC

- Smt. C. Naga Rani, IAS, Director, Technical Education

- Smt. B. Lavanya Veni, IAS, Director, Employment & Training

- Shri. G. Balasubramanyam, JD, DET

- Shri. Nirmal Kumar Priya, JD, CTE

- Dr. B. Parthasaradhi, ED, SEEDAP

- Dr. D.V.Ramakoti Reddy, ED, APSSDC

- Shri. M.K.V.Srinivasulu, ED, APSSDC

- Smt. B.R. Kranthi Kumari, FO, APSSDC

- Shri. K.V.Nagaraja, ADG, NAC

- Other team members from respective departments

- Virtually - Principals of Skill Hubs, District functionaries of respective departments

Agenda:

A review meeting has been convened by the Principal Secretary, SD&T Dept. on Skill Hubs and Skill Colleges. The agenda items of the meeting are as follows:

- Co-ordination among departments working under skill development and vocational trainings

- Skill Hubs program - status of implementation

- Skill Hubs program – status of planning - Phase II

- Industry connect

- Job melas implementation

- Co-ordination among Stakeholder Departments under SD&T Dept.

- All the stakeholder departments (APSSDC, DET, DTE, NAC, SEEDAP) under Skills Development & Training Department shall work in coordination.

- MD&CEO, APSSDC shall submit the abstract of employees of APSSDC (State HQ, District Wise) along with List of such employees (Name, Designation, Work Allocation) to Prl. Secy., SD&T by 05/05/2022.

- Executive Director, SEEDAP shall coordinate with OSD-HR, APSSDC for mapping of all SEEDAP resources at District Level to Skill Hubs by 05/05/2022.

- ADG NAC shall coordinate with OSD-HR, APSSDC for mapping of NAC resources at District Level to Skill Hubs by 05/05/2022.

- All departments under SD&T shall focus on Skill Cascade with priority on successful launch of Skill Hubs.

Action: OSD(HR)-APSSDC, ED-SEEDAP, ADG NAC

- Skill Hubs TP & TC Registration

- Separate Bank Accounts should be opened by each of the institution identified as Skill Hub for handling finances pertaining to the Skill Cascade Program.

- Various options for arranging good internet facility at skill hubs shall be explored.

- Discussion shall be held with concerned department for ensuring proper internet connectivity to all the locations.

Action: ED (Skill Hubs) APSSDC, GM(T1)-APSSDC

- TOT To Trainers and Registration on TakshashilaPortal

- All stakeholder departments (APSSDC, SEEDAP, NAC, DET, CTE, CCE) shall ensure participation of the trainers proposed for Skill Hubs in TOT Program without fail.

- The attendance of TOT program shall be maintained and submitted to Prl. Secy., SD&T on daily basis.

- All cases of non-attendance of TOT Program by trainers shall be brought to the notice of respective HoDs who shall intimate the same to Prl. Secy., SD&T along with action initiated for such laxity.

- Provision for capturing TOT attendance on Skill India Portal shall be explored.

- The TOT shall be completed before 12th September 2022.

- Efforts should be made to train all district level staff of APSSDC, SEEDAP, NAC, DET (DEO Office) in atleast one QP Pack of Skill Hubs through TOT Program by 30/09/2022.

- Based on the area of interest and educational background, all these resources shall attend TOT and become certified trainers. Budget pertaining to TOTs shall be borne by the respective departments for their staff.

- All district level staff of APSSDC, JDMs, JRPs from SEEDAP, JEO’s from DET, and NAC Trainers, shall be registered in Takshashila Portal as trainers by 30/09/2022.

- E-office file shall be circulated on the same to Prl. Secy., SD&T Dept by the respective HoDs.

Action: MD APSSDC, CEO / ED SEEDAP, ADG NAC, DET, State Engagement Officer-NSDC

- Nodal Officers for Sectors

- The following nodal officers are allocated for the below mentioned sectors for carrying out all activities pertaining to Skill Cascade Programme.

| SN | Sector | Nodal Officer |
| --- | --- | --- |
|  | Pharma, Healthcare and Life Sciences | Dr. G ParthaSarathi, ED, SEEDAP |
|  | Food Processing |  |
|  | Infrastructure Equipment & Capital Goods | Mr. M. Indra Kiran, Director, NAC |
|  | Media & Entertainment |  |
|  | Aerospace, Aviation and Strategic, Drones | Mr. Motilal Naik |
|  | Construction and Plumbing | Mr. K.V. Nagaraja, ADG, NAC |
|  | Power and Renewables |  |
|  | Banking, Financial Services & Insurance (BFSI) | Mr. L. Prasad Babu, SMM SEEDAP |
|  | Hydrocarbon, Ports Logistics |  |
|  | IT-ITeS | Mr. Ravi Gujjula, CGM-T, APSSDC |
|  | Tourism & Hospitality | Mr. M. Vijaya Kumar, SMM, SEEDAP |
|  | Automobile & EV |  |
|  | Agriculture | Smt. B.R. Kranthi Kumari, FO, APSSDC |
|  | Animal Husbandry and Dairy |  |
|  | Fisheries |  |
|  | NFTP and Forestry | Smt. D. Lakshmi Devi, SMM, SEEDAP |
|  | Beauty & Wellness |  |
|  | Textiles & Handicrafts, Leather | Smt.H. Bharathi, GM, APSSDC |
|  | Telecom and Electronics |  |

- The nodal officers shall be responsible for following activities.

  - Visit all the Skill Hubs (Phase 1 as well as proposed for Phase 2) and Interim Skill Colleges for their sectors and monitor the progress of the skilling programs and activities.

  - Coordinate with Sector Skill Councils and Line Departments, Industries Department, APIIC, APEDB, APEITA, APNRTS to identify skilling and training activities that shall cater to sector / industry demand and lead to employment.

  - Identify the champion employers in their respective sectors.

  - Identify stakeholders including industries, industry associations, line department nodal officers, Civil Society Organisations in skilling etc. and propose Sectoral Advisory Groups to be formed under the leadership of lead industries.

  - Visit existing skilling and training infrastructure of the industries and propose these as industry led Skill Spokes where Training Partners and Training Centers shall be provided by the industry itself. The Nodal Officers shall assist in bringing these centres as Skill Spokes under Skill Cascade Programme by registering them on Skill India Portal and initiate the suitable training programmes with relevant QPs.

  - The nodal officers shall form their own internal teams to work on the above said activities pertaining sectors allocated to them.

  - Mr. Gopinadh, GM APSSDC shall look after corporate connect activities.

  - E-office file shall be circulated for conducting meetings with industries.

Action: ED(Skill Hubs)-APSSDC, GM (Gopinadh), Sectoral Nodal Officers

- Skill Hubs Civil Works

- After 10th September 2022, once the skill hubs are ready with all required facilities, the training shall start.

- Location wise contact details of AEs, R&BDept. shall be added to the skill hubs slides and shall be shared with all stakeholders.

- Any issues related to Civil works shall be informed to ED (Skill Hubs), APSSDC for resolution. No demolition of existing infrastructure should be taken up.

- Wherever the additional civil works are required (in addition to the APSAB estimations), the principal and DSDO shall discuss and send the request to MD&CEO, APSSDC. MD&CEO, APSSDC may consider the request based on the need.

- ED, APSSDC shall share the location wise layout plans and civil requirements drawn by APSAB to all the principals of Skill Hubs.

- The biometric devices available at the institutes (ITIs, Polytechnics, Degree Colleges) shall be used for capturing the student and trainer attendance.

Action: ED(Skill Hubs)-APSSDC, Principals of Skill Hubs, OSD-APSAB

- Skill Hubs Mobilization Strategy

- Letter communication shall be sent to district administration, GSWS Department and Panchayati Raj Department seeking their support for mobilizing the candidates.

- The candidate’s registration app may be launched by 5th September 2022. Modalities for integrating interface to GSWS department shall be worked out meanwhile.

- The data pertaining to candidates mobilized for 1st batch shall be integrated into the application post development.

Action: ED-APSSDC

- Skill India International Network (SIIN):

- Ms. Kranthi, GM, APSSDC shall look after Skill India International Network (SIIN) project and shall work in collaboration with GM, OMCAP and team who is working on overseas placements.

Action: GM(Kranthi)-APSSDC, GM-OMCAP

- Joint Placement Calendar:

- APSSDC in coordination with Department of Employment & Training and SEEDAP shall prepare a Joint Placement Calendar which shall be followed by the respective departments and avoid duplication of efforts while conducting the Job Melas.

- The Job Melas shall be conducted in every district covering different Assembly Constituencies on every Tuesday and Friday.

- A common venue (only government premises) shall be identified in each AC across 175 ACs for conducting Job Melas by District Employment Officers (DET) and DSDOs and JDMs together.

- The mobile app which has been created for candidate registration shall populate the Joint Placement Calendar data.

- District Employment Officers (DET) shall coordinate the placement and employment activities (Job Melas) with DSDOs and JDMs and submit weekly reports on behalf of the entire team through Director Employment and Training.

Action: DET, MD APSSDC, ED-SEEDAP

***